## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Beta | TSK-001 | Task 001 | 2025-06-30 |  | 2025-06-30 | 2025-08-20 | 51 | FALSE | 0 | 0 | 70 | In Progress | FALSE | TRUE | TRUE | L | 2 | On Critical Path (+2 points) | Update_001
Beta | TSK-002 | Task 002 | 2025-02-13 |  | 2025-02-11 | 2025-02-27 | 16 | FALSE | 0 | 0 |  | Not Started | TRUE | FALSE | TRUE | H | 3 | Risk Level: H (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-003 | Task 003 | 2025-09-11 |  | 2025-09-11 | 2025-11-01 | 51 | FALSE | 0 | 0 | 3 | Complete | TRUE | FALSE | FALSE |  | 1 | Milestone Task (+1 point) | Update_001
Beta | TSK-004 | Task 004 | 2025-05-01 |  | 2025-05-04 | 2025-07-02 | 59 | FALSE | 0 | 0 |  | Not Started | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-005 | Task 005 | 2025-09-29 | 2025-11-14 | 2025-09-29 | 2025-11-11 | 43 | TRUE | 3 | 7 | 1 | Complete | FALSE | FALSE | FALSE | Medium | 2 | Delayed by 3 days (+1 points); Risk Level: Medium (+1 points) | Update_001
Beta | TSK-006 | Task 006 | 2025-01-02 |  | 2025-01-02 | 2025-02-03 | 32 | FALSE | 0 | 0 | 2% | In Progress | FALSE | TRUE | TRUE | High | 4 | Risk Level: High (+2 points); On Critical Path (+2 points) | Update_001
Beta | TSK-007 | Task 007 | 2025-05-15 |  | 2025-05-12 | 2025-06-13 | 32 | FALSE | 0 | 0 | 49 | In Progress | TRUE | FALSE | TRUE | Low | 1 | Milestone Task (+1 point) | Update_001
Beta | TSK-008 | Task 008 | 2025-01-04 |  | 2025-01-02 | 2025-02-12 | 41 | FALSE | 0 | 0 | 47 | In Progress | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-009 | Task 009 | 2025-10-18 |  | 2025-10-15 | 2025-11-29 | 45 | FALSE | 0 | 0 |  | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_001
Beta | TSK-010 | Task 010 | 2024-12-20 |  | 2024-12-18 | 2024-12-29 | 11 | FALSE | 0 | 0 | 44% | IP | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-011 | Task 011 | 2025-10-22 |  | 2025-10-22 | 2025-11-14 | 23 | FALSE | 0 | 0 | 41% | Not Started | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-012 | Task 012 | 2025-08-06 |  | 2025-08-05 | 2025-09-08 | 34 | FALSE | 0 | 0 | 24% |  | FALSE | TRUE | TRUE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-013 | Task 013 | 2025-03-25 |  | 2025-03-28 | 2025-05-20 | 53 | FALSE | 0 | 0 | 24 |  | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-014 | Task 014 | 2025-08-28 |  | 2025-08-31 | 2025-09-16 | 16 | FALSE | 0 | 0 | 86 | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_001
Beta | TSK-015 | Task 015 | 2025-03-20 | 2025-04-11 | 2025-03-22 | 2025-04-12 | 21 | FALSE | -1 | -4.8 | Complete | Complete | FALSE | TRUE | FALSE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-016 | Task 016 | 2025-04-12 |  | 2025-04-13 | 2025-06-11 | 59 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-017 | Task 017 | 2024-12-03 | 2025-01-21 | 2024-12-05 | 2025-01-24 | 50 | FALSE | -3 | -6 | 100% | Complete | FALSE | FALSE | FALSE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-018 | Task 018 | 2025-04-02 | 2025-05-18 | 2025-03-31 | 2025-04-30 | 30 | TRUE | 18 | 60 | Complete | Complete | FALSE | TRUE | FALSE |  | 4 | Delayed by 18 days (+2 points); On Critical Path (+2 points) | Update_001
Beta | TSK-019 | Task 019 | 2024-11-05 |  | 2024-11-05 | 2024-12-30 | 55 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-020 | Task 020 | 2025-09-23 |  | 2025-09-25 | 2025-10-25 | 30 | FALSE | 0 | 0 |  | Not Started | TRUE | FALSE | TRUE | H | 3 | Risk Level: H (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-021 | Task 021 | 2025-10-17 |  | 2025-10-17 | 2025-12-06 | 50 | FALSE | 0 | 0 | 15% | Complete | TRUE | TRUE | FALSE | L | 3 | On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-022 | Task 022 | 2024-12-07 |  | 2024-12-10 | 2025-01-05 | 26 | FALSE | 0 | 0 | 39 | IP | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-023 | Task 023 | 2025-04-25 |  | 2025-04-22 | 2025-06-03 | 42 | FALSE | 0 | 0 | 47 |  | FALSE | FALSE | TRUE |  | 0 |  | Update_001
Beta | TSK-024 | Task 024 | 2025-03-27 |  | 2025-03-25 | 2025-04-16 | 22 | FALSE | 0 | 0 | 67 | In Progress | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-025 | Task 025 | 2025-10-09 |  | 2025-10-09 | 2025-11-14 | 36 | FALSE | 0 | 0 |  | Not Started | TRUE | FALSE | TRUE |  | 1 | Milestone Task (+1 point) | Update_001
Beta | TSK-026 | Task 026 | 2025-05-14 |  | 2025-05-17 | 2025-05-27 | 10 | FALSE | 0 | 0 | 39 | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_001
Beta | TSK-027 | Task 027 | 2025-06-09 |  | 2025-06-06 | 2025-07-17 | 41 | FALSE | 0 | 0 | 50% | In Progress | FALSE | FALSE | TRUE |  | 0 |  | Update_001
Beta | TSK-028 | Task 028 | 2025-07-10 |  | 2025-07-12 | 2025-08-06 | 25 | FALSE | 0 | 0 | 60 | Not Started | TRUE | TRUE | TRUE |  | 3 | On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-029 | Task 029 | 2025-02-23 | 2025-03-10 | 2025-02-20 | 2025-03-03 | 11 | TRUE | 7 | 63.6 | 1 | Complete | FALSE | FALSE | FALSE | L | 1 | Delayed by 7 days (+1 points) | Update_001
Beta | TSK-030 | Task 030 | 2024-11-05 |  | 2024-11-04 | 2024-11-26 | 22 | FALSE | 0 | 0 |  | IP | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-031 | Task 031 | 2024-12-19 |  | 2024-12-22 | 2025-02-07 | 47 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-032 | Task 032 | 2025-07-19 |  | 2025-07-16 | 2025-08-03 | 18 | FALSE | 0 | 0 |  |  | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-033 | Task 033 | 2025-04-02 |  | 2025-03-30 | 2025-05-15 | 46 | FALSE | 0 | 0 | 27 | In Progress | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-034 | Task 034 | 2025-03-27 |  | 2025-03-26 | 2025-04-12 | 17 | FALSE | 0 | 0 | 31% |  | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-035 | Task 035 | 2025-09-16 |  | 2025-09-16 | 2025-11-01 | 46 | FALSE | 0 | 0 |  | Complete | FALSE | TRUE | FALSE | Low | 2 | On Critical Path (+2 points) | Update_001
Beta | TSK-036 | Task 036 | 2025-05-19 |  | 2025-05-21 | 2025-07-16 | 56 | FALSE | 0 | 0 | 18% | IP | TRUE | FALSE | TRUE | H | 3 | Risk Level: H (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-037 | Task 037 | 2025-03-24 |  | 2025-03-25 | 2025-04-05 | 11 | FALSE | 0 | 0 | 31 | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-038 | Task 038 | 2025-07-02 |  | 2025-07-03 | 2025-08-04 | 32 | FALSE | 0 | 0 | 0.17237 | IP | FALSE | TRUE | TRUE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-039 | Task 039 | 2025-05-18 |  | 2025-05-18 | 2025-06-20 | 33 | FALSE | 0 | 0 | 0.50833 | In Progress | FALSE | TRUE | TRUE | Low | 2 | On Critical Path (+2 points) | Update_001
Beta | TSK-040 | Task 040 | 2025-03-27 |  | 2025-03-26 | 2025-05-22 | 57 | FALSE | 0 | 0 |  | IP | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-041 | Task 041 | 2025-07-21 |  | 2025-07-24 | 2025-09-10 | 48 | FALSE | 0 | 0 |  | Complete | FALSE | FALSE | FALSE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-042 | Task 042 | 2025-07-23 |  | 2025-07-21 | 2025-09-09 | 50 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-043 | Task 043 | 2025-09-22 |  | 2025-09-21 | 2025-10-16 | 25 | FALSE | 0 | 0 | 64% | IP | FALSE | TRUE | TRUE | High | 4 | Risk Level: High (+2 points); On Critical Path (+2 points) | Update_001
Beta | TSK-044 | Task 044 | 2025-03-24 |  | 2025-03-27 | 2025-04-18 | 22 | FALSE | 0 | 0 |  | Complete | FALSE | FALSE | FALSE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-045 | Task 045 | 2025-07-20 |  | 2025-07-18 | 2025-08-12 | 25 | FALSE | 0 | 0 |  |  | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-046 | Task 046 | 2024-12-15 |  | 2024-12-16 | 2025-01-13 | 28 | FALSE | 0 | 0 | 24 | Complete | FALSE | TRUE | FALSE | Low | 2 | On Critical Path (+2 points) | Update_001
Beta | TSK-047 | Task 047 | 2025-02-11 |  | 2025-02-10 | 2025-03-05 | 23 | FALSE | 0 | 0 | 33% | Not Started | FALSE | TRUE | TRUE | H | 4 | Risk Level: H (+2 points); On Critical Path (+2 points) | Update_001
Beta | TSK-048 | Task 048 | 2024-12-20 |  | 2024-12-18 | 2025-01-16 | 29 | FALSE | 0 | 0 | 0.2713 | Complete | TRUE | TRUE | FALSE | High | 5 | Risk Level: High (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-049 | Task 049 | 2025-03-15 |  | 2025-03-12 | 2025-03-28 | 16 | FALSE | 0 | 0 | 42% | IP | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-050 | Task 050 | 2025-09-17 |  | 2025-09-17 | 2025-10-18 | 31 | FALSE | 0 | 0 | 23% | In Progress | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-051 | Task 051 | 2024-12-25 |  | 2024-12-24 | 2025-01-18 | 25 | FALSE | 0 | 0 | 41% | Not Started | TRUE | FALSE | TRUE | H | 3 | Risk Level: H (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-052 | Task 052 | 2025-09-06 | 2025-10-31 | 2025-09-04 | 2025-10-31 | 57 | FALSE | 0 | 0 | Complete | Complete | TRUE | TRUE | FALSE | H | 5 | Risk Level: H (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-053 | Task 053 | 2025-04-05 |  | 2025-04-06 | 2025-04-28 | 22 | FALSE | 0 | 0 | 55% |  | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-054 | Task 054 | 2025-08-18 |  | 2025-08-17 | 2025-10-09 | 53 | FALSE | 0 | 0 |  |  | TRUE | TRUE | TRUE | H | 5 | Risk Level: H (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-055 | Task 055 | 2025-09-10 |  | 2025-09-13 | 2025-10-29 | 46 | FALSE | 0 | 0 | 14% | Complete | FALSE | FALSE | FALSE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-056 | Task 056 | 2025-07-02 |  | 2025-07-03 | 2025-07-31 | 28 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-057 | Task 057 | 2025-02-22 |  | 2025-02-22 | 2025-04-23 | 60 | FALSE | 0 | 0 | 0.94088 | In Progress | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-058 | Task 058 | 2025-10-03 |  | 2025-09-30 | 2025-11-10 | 41 | FALSE | 0 | 0 | 2 | In Progress | TRUE | FALSE | TRUE |  | 1 | Milestone Task (+1 point) | Update_001
Beta | TSK-059 | Task 059 | 2024-12-30 |  | 2025-01-02 | 2025-02-24 | 53 | FALSE | 0 | 0 | 19% | IP | FALSE | TRUE | TRUE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-060 | Task 060 | 2025-07-28 |  | 2025-07-29 | 2025-09-25 | 58 | FALSE | 0 | 0 | 16% |  | FALSE | TRUE | TRUE | L | 2 | On Critical Path (+2 points) | Update_001
Beta | TSK-061 | Task 061 | 2025-03-17 |  | 2025-03-18 | 2025-04-16 | 29 | FALSE | 0 | 0 | 31% | IP | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-062 | Task 062 | 2025-04-18 |  | 2025-04-19 | 2025-06-01 | 43 | FALSE | 0 | 0 | 50% |  | FALSE | TRUE | TRUE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-063 | Task 063 | 2025-10-16 |  | 2025-10-13 | 2025-11-26 | 44 | FALSE | 0 | 0 | 79% | IP | FALSE | FALSE | TRUE | H | 2 | Risk Level: H (+2 points) | Update_001
Beta | TSK-064 | Task 064 | 2025-03-05 |  | 2025-03-08 | 2025-04-04 | 27 | FALSE | 0 | 0 | Complete | Complete | TRUE | TRUE | FALSE | Low | 3 | On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-065 | Task 065 | 2025-10-10 |  | 2025-10-12 | 2025-12-07 | 56 | FALSE | 0 | 0 |  | Not Started | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-066 | Task 066 | 2025-09-27 |  | 2025-09-25 | 2025-11-11 | 47 | FALSE | 0 | 0 |  |  | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_001
Beta | TSK-067 | Task 067 | 2025-05-02 |  | 2025-05-03 | 2025-06-13 | 41 | FALSE | 0 | 0 | 0.83336 | Not Started | FALSE | TRUE | TRUE | H | 4 | Risk Level: H (+2 points); On Critical Path (+2 points) | Update_001
Beta | TSK-068 | Task 068 | 2025-09-05 |  | 2025-09-07 | 2025-09-29 | 22 | FALSE | 0 | 0 | 7 |  | FALSE | FALSE | TRUE | Low | 0 |  | Update_001
Beta | TSK-069 | Task 069 | 2025-03-11 |  | 2025-03-14 | 2025-04-10 | 27 | FALSE | 0 | 0 | 0.45189 | In Progress | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-070 | Task 070 | 2025-01-08 |  | 2025-01-11 | 2025-02-14 | 34 | FALSE | 0 | 0 |  |  | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_001
Beta | TSK-071 | Task 071 | 2025-07-05 |  | 2025-07-08 | 2025-08-18 | 41 | FALSE | 0 | 0 | 9 | In Progress | TRUE | TRUE | TRUE | H | 5 | Risk Level: H (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_001
Beta | TSK-072 | Task 072 | 2025-03-15 |  | 2025-03-18 | 2025-04-19 | 32 | FALSE | 0 | 0 |  | Not Started | FALSE | FALSE | TRUE | L | 0 |  | Update_001
Beta | TSK-073 | Task 073 | 2024-12-03 | 2025-01-09 | 2024-12-04 | 2025-01-06 | 33 | TRUE | 3 | 9.1 | Complete | Complete | FALSE | TRUE | FALSE | Medium | 4 | Delayed by 3 days (+1 points); Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_001
Beta | TSK-074 | Task 074 | 2025-07-08 |  | 2025-07-08 | 2025-07-31 | 23 | FALSE | 0 | 0 | 80% | Not Started | TRUE | FALSE | TRUE | L | 1 | Milestone Task (+1 point) | Update_001
Beta | TSK-075 | Task 075 | 2025-07-10 |  | 2025-07-13 | 2025-09-05 | 54 | FALSE | 0 | 0 | 100% |  | FALSE | TRUE | TRUE | H | 4 | Risk Level: H (+2 points); On Critical Path (+2 points) | Update_001