## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Delta | TSK-001 | Task 001 | 2024-12-20 | 2025-04-20 | 2024-12-22 | 2025-02-20 | 60 | TRUE | 58 | 96.7 | Complete | Complete | FALSE | FALSE | FALSE |  | 5 | Delayed by 58 days (+5 points) | Update_009
Delta | TSK-002 | Task 002 | 2025-03-23 | 2025-05-16 | 2025-03-22 | 2025-04-12 | 21 | TRUE | 33 | 157.1 | Complete | Complete | TRUE | FALSE | FALSE | High | 7 | Delayed by 33 days (+4 points); Risk Level: High (+2 points); Milestone Task (+1 point) | Update_009
Delta | TSK-003 | Task 003 | 2025-04-13 | 2025-04-28 | 2025-04-10 | 2025-04-20 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-004 | Task 004 | 2025-03-22 | 2025-05-13 | 2025-03-22 | 2025-04-21 | 30 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-005 | Task 005 | 2025-03-09 | 2025-04-19 | 2025-03-12 | 2025-04-08 | 27 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_009
Delta | TSK-006 | Task 006 | 2024-12-30 | 2025-02-26 | 2024-12-30 | 2025-01-28 | 29 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-007 | Task 007 | 2024-11-19 | 2025-01-19 | 2024-11-20 | 2024-12-03 | 13 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-008 | Task 008 | 2025-05-01 | 2025-07-16 | 2025-05-02 | 2025-06-22 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_009
Delta | TSK-009 | Task 009 | 2025-03-14 | 2025-05-20 | 2025-03-13 | 2025-03-27 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-010 | Task 010 | 2025-10-17 | 2025-12-28 | 2025-10-18 | 2025-11-24 | 37 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-011 | Task 011 | 2025-09-02 | 2025-10-15 | 2025-09-02 | 2025-09-19 | 17 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-012 | Task 012 | 2025-10-16 | 2026-01-28 | 2025-10-18 | 2025-12-12 | 55 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-013 | Task 013 | 2024-12-14 | 2025-04-02 | 2024-12-11 | 2025-01-24 | 44 | TRUE | 67 | 152.3 | 100% | Complete | FALSE | FALSE | FALSE | L | 5 | Delayed by 67 days (+5 points) | Update_009
Delta | TSK-014 | Task 014 | 2025-01-27 | 2025-04-03 | 2025-01-24 | 2025-02-16 | 23 | TRUE | 45 | 195.7 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 6 | Delayed by 45 days (+5 points); Risk Level: Medium (+1 points) | Update_009
Delta | TSK-015 | Task 015 | 2025-04-24 | 2025-08-12 | 2025-04-24 | 2025-06-23 | 60 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-016 | Task 016 | 2025-02-06 | 2025-05-02 | 2025-02-07 | 2025-04-07 | 59 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | H | 0 |  | Update_009
Delta | TSK-017 | Task 017 | 2025-04-29 | 2025-06-13 | 2025-04-28 | 2025-06-03 | 36 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-018 | Task 018 | 2025-01-19 | 2025-03-19 | 2025-01-19 | 2025-02-15 | 27 | TRUE | 31 | 114.8 | 100% | Complete | FALSE | FALSE | FALSE | High | 6 | Delayed by 31 days (+4 points); Risk Level: High (+2 points) | Update_009
Delta | TSK-019 | Task 019 | 2025-01-29 | 2025-06-05 | 2025-02-01 | 2025-03-02 | 29 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-020 | Task 020 | 2024-12-03 | 2025-03-17 | 2024-12-06 | 2025-02-01 | 57 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_009
Delta | TSK-021 | Task 021 | 2025-01-29 | 2025-04-24 | 2025-01-31 | 2025-02-25 | 25 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_009
Delta | TSK-022 | Task 022 | 2025-06-30 | 2025-08-17 | 2025-06-30 | 2025-07-23 | 23 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_009
Delta | TSK-023 | Task 023 | 2025-03-03 | 2025-04-14 | 2025-03-04 | 2025-04-18 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-024 | Task 024 | 2025-03-05 | 2025-03-13 | 2025-03-03 | 2025-04-23 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-025 | Task 025 | 2025-08-25 | 2025-10-22 | 2025-08-22 | 2025-09-09 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-026 | Task 026 | 2025-04-23 | 2025-06-09 | 2025-04-21 | 2025-05-22 | 31 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-027 | Task 027 | 2025-01-24 | 2025-05-12 | 2025-01-21 | 2025-03-18 | 56 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-028 | Task 028 | 2025-03-02 | 2025-04-09 | 2025-03-01 | 2025-03-25 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-029 | Task 029 | 2024-12-22 | 2025-03-24 | 2024-12-25 | 2025-02-13 | 50 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_009
Delta | TSK-030 | Task 030 | 2025-09-16 | 2025-11-17 | 2025-09-16 | 2025-09-30 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-031 | Task 031 | 2025-07-26 | 2025-08-31 | 2025-07-24 | 2025-08-11 | 18 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-032 | Task 032 | 2024-11-09 | 2025-01-13 | 2024-11-07 | 2024-12-01 | 24 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-033 | Task 033 | 2025-04-30 | 2025-05-16 | 2025-05-03 | 2025-05-13 | 10 | TRUE | 2 | 20 | Complete | Complete | FALSE | FALSE | FALSE | Low | 1 | Delayed by 2 days (+1 points) | Update_009
Delta | TSK-034 | Task 034 | 2024-12-02 | 2025-02-27 | 2024-11-30 | 2025-01-09 | 40 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-035 | Task 035 | 2025-02-03 | 2025-03-01 | 2025-02-03 | 2025-02-17 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-036 | Task 036 | 2025-07-10 | 2025-08-26 | 2025-07-07 | 2025-07-26 | 19 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_009
Delta | TSK-037 | Task 037 | 2024-11-26 | 2025-01-07 | 2024-11-26 | 2024-12-15 | 19 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-038 | Task 038 | 2025-05-16 | 2025-08-08 | 2025-05-18 | 2025-07-13 | 56 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-039 | Task 039 | 2025-08-23 | 2025-11-02 | 2025-08-24 | 2025-09-10 | 17 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-040 | Task 040 | 2025-10-14 | 2026-01-03 | 2025-10-16 | 2025-11-09 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-041 | Task 041 | 2025-08-07 | 2025-10-17 | 2025-08-08 | 2025-09-08 | 31 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-042 | Task 042 | 2025-07-05 | 2025-09-13 | 2025-07-07 | 2025-08-16 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_009
Delta | TSK-043 | Task 043 | 2025-05-14 | 2025-06-28 | 2025-05-12 | 2025-05-30 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-044 | Task 044 | 2025-02-17 | 2025-05-06 | 2025-02-18 | 2025-04-12 | 53 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_009
Delta | TSK-045 | Task 045 | 2025-09-13 | 2025-12-07 | 2025-09-16 | 2025-11-11 | 56 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-046 | Task 046 | 2025-03-19 | 2025-05-18 | 2025-03-20 | 2025-03-30 | 10 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-047 | Task 047 | 2025-02-20 | 2025-05-13 | 2025-02-22 | 2025-03-06 | 12 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-048 | Task 048 | 2024-12-11 | 2025-01-18 | 2024-12-14 | 2024-12-25 | 11 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-049 | Task 049 | 2024-12-28 | 2025-01-27 | 2024-12-27 | 2025-01-14 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-050 | Task 050 | 2025-03-16 | 2025-06-11 | 2025-03-13 | 2025-05-04 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-051 | Task 051 | 2025-09-06 | 2025-11-03 | 2025-09-07 | 2025-09-19 | 12 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-052 | Task 052 | 2025-10-19 | 2025-11-28 | 2025-10-20 | 2025-10-31 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-053 | Task 053 | 2025-03-12 | 2025-05-28 | 2025-03-11 | 2025-05-06 | 56 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-054 | Task 054 | 2025-06-20 | 2025-08-15 | 2025-06-19 | 2025-08-04 | 46 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_009
Delta | TSK-055 | Task 055 | 2025-07-24 | 2025-08-21 | 2025-07-26 | 2025-08-12 | 17 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_009
Delta | TSK-056 | Task 056 | 2025-03-25 | 2025-05-30 | 2025-03-27 | 2025-04-11 | 15 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-057 | Task 057 | 2025-02-08 | 2025-03-24 | 2025-02-09 | 2025-03-02 | 21 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-058 | Task 058 | 2025-05-12 | 2025-06-28 | 2025-05-10 | 2025-06-23 | 44 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_009
Delta | TSK-059 | Task 059 | 2025-07-24 | 2025-09-12 | 2025-07-26 | 2025-08-27 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-060 | Task 060 | 2024-12-06 | 2025-02-15 | 2024-12-08 | 2024-12-26 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-061 | Task 061 | 2025-10-18 | 2026-01-03 | 2025-10-15 | 2025-11-25 | 41 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-062 | Task 062 | 2025-05-29 | 2025-06-08 | 2025-05-30 | 2025-06-17 | 18 | FALSE | -10 | -55.6 | 1 | Complete | FALSE | FALSE | FALSE | H | 2 | Risk Level: H (+2 points) | Update_009
Delta | TSK-063 | Task 063 | 2025-07-16 | 2025-08-09 | 2025-07-14 | 2025-08-13 | 30 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_009
Delta | TSK-064 | Task 064 | 2025-07-24 | 2025-09-28 | 2025-07-23 | 2025-09-19 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_009
Delta | TSK-065 | Task 065 | 2025-01-15 | 2025-03-30 | 2025-01-17 | 2025-02-13 | 27 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_009
Delta | TSK-066 | Task 066 | 2025-03-12 | 2025-05-15 | 2025-03-10 | 2025-04-13 | 34 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-067 | Task 067 | 2025-08-26 | 2026-01-11 | 2025-08-26 | 2025-10-24 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-068 | Task 068 | 2025-10-08 | 2025-12-12 | 2025-10-10 | 2025-12-02 | 53 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_009
Delta | TSK-069 | Task 069 | 2025-03-03 | 2025-04-12 | 2025-03-06 | 2025-03-20 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-070 | Task 070 | 2025-03-12 | 2025-05-23 | 2025-03-10 | 2025-04-03 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_009
Delta | TSK-071 | Task 071 | 2025-07-01 | 2025-08-30 | 2025-07-03 | 2025-08-21 | 49 | TRUE | 8 | 16.3 | 100% | Complete | FALSE | FALSE | FALSE | Low | 1 | Delayed by 8 days (+1 points) | Update_009
Delta | TSK-072 | Task 072 | 2024-11-15 | 2024-12-25 | 2024-11-12 | 2024-11-27 | 15 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_009
Delta | TSK-073 | Task 073 | 2025-05-27 | 2025-08-07 | 2025-05-28 | 2025-06-23 | 26 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_009
Delta | TSK-074 | Task 074 | 2025-01-26 | 2025-03-16 | 2025-01-29 | 2025-02-25 | 27 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_009
Delta | TSK-075 | Task 075 | 2025-07-14 | 2025-09-26 | 2025-07-16 | 2025-09-13 | 59 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | L | 0 |  | Update_009