## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Gamma | TSK-001 | Task 001 | 2025-01-12 | 2025-03-05 | 2025-01-10 | 2025-02-23 | 44 | TRUE | 9 | 20.5 | 100% | Complete | FALSE | TRUE | FALSE | L | 3 | Delayed by 9 days (+1 points); On Critical Path (+2 points) | Update_010
Gamma | TSK-002 | Task 002 | 2025-04-28 | 2025-06-06 | 2025-04-28 | 2025-06-11 | 44 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-003 | Task 003 | 2025-01-19 | 2025-04-08 | 2025-01-21 | 2025-02-22 | 32 | TRUE | 44 | 137.5 | 100% | Complete | FALSE | TRUE | FALSE |  | 7 | Delayed by 44 days (+5 points); On Critical Path (+2 points) | Update_010
Gamma | TSK-004 | Task 004 | 2025-03-06 | 2025-07-05 | 2025-03-03 | 2025-04-04 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Gamma | TSK-005 | Task 005 | 2025-08-27 | 2025-10-16 | 2025-08-25 | 2025-10-10 | 46 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-006 | Task 006 | 2024-11-09 | 2025-01-16 | 2024-11-12 | 2024-12-20 | 38 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-007 | Task 007 | 2025-09-22 | 2025-12-06 | 2025-09-23 | 2025-10-16 | 23 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-008 | Task 008 | 2025-02-28 | 2025-04-22 | 2025-03-01 | 2025-03-15 | 14 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-009 | Task 009 | 2025-05-30 | 2025-07-14 | 2025-05-29 | 2025-06-17 | 19 | TRUE | 26 | 136.8 | Complete | Complete | FALSE | TRUE | FALSE | H | 7 | Delayed by 26 days (+3 points); Risk Level: H (+2 points); On Critical Path (+2 points) | Update_010
Gamma | TSK-010 | Task 010 | 2025-04-23 | 2025-07-19 | 2025-04-26 | 2025-06-13 | 48 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-011 | Task 011 | 2025-06-04 | 2025-07-28 | 2025-06-02 | 2025-07-20 | 48 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-012 | Task 012 | 2025-07-28 | 2025-09-14 | 2025-07-25 | 2025-08-15 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-013 | Task 013 | 2025-07-24 | 2025-09-18 | 2025-07-25 | 2025-08-28 | 34 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-014 | Task 014 | 2025-06-15 | 2025-08-22 | 2025-06-12 | 2025-07-10 | 28 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-015 | Task 015 | 2025-03-10 | 2025-07-01 | 2025-03-10 | 2025-04-30 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-016 | Task 016 | 2025-01-05 | 2025-02-28 | 2025-01-03 | 2025-01-17 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_010
Gamma | TSK-017 | Task 017 | 2025-04-12 | 2025-05-26 | 2025-04-15 | 2025-05-05 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-018 | Task 018 | 2025-07-12 | 2025-07-26 | 2025-07-13 | 2025-07-26 | 13 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-019 | Task 019 | 2025-07-10 | 2025-10-07 | 2025-07-13 | 2025-08-13 | 31 | TRUE | 54 | 174.2 | 100% | Complete | FALSE | FALSE | FALSE | H | 7 | Delayed by 54 days (+5 points); Risk Level: H (+2 points) | Update_010
Gamma | TSK-020 | Task 020 | 2025-09-10 | 2025-09-24 | 2025-09-12 | 2025-10-14 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-021 | Task 021 | 2024-12-16 | 2025-02-10 | 2024-12-18 | 2025-01-16 | 29 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-022 | Task 022 | 2025-01-15 | 2025-03-18 | 2025-01-13 | 2025-03-13 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-023 | Task 023 | 2025-08-19 | 2025-11-12 | 2025-08-17 | 2025-10-14 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_010
Gamma | TSK-024 | Task 024 | 2025-07-16 | 2025-11-08 | 2025-07-19 | 2025-08-09 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Gamma | TSK-025 | Task 025 | 2025-05-04 | 2025-07-05 | 2025-05-05 | 2025-05-16 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-026 | Task 026 | 2025-08-10 | 2025-09-21 | 2025-08-11 | 2025-08-21 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Gamma | TSK-027 | Task 027 | 2025-08-10 | 2025-10-15 | 2025-08-07 | 2025-08-22 | 15 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Gamma | TSK-028 | Task 028 | 2024-11-22 | 2025-02-25 | 2024-11-24 | 2025-01-05 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-029 | Task 029 | 2024-12-11 | 2025-02-06 | 2024-12-13 | 2024-12-31 | 18 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-030 | Task 030 | 2025-01-03 | 2025-01-23 | 2025-01-01 | 2025-02-02 | 32 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-031 | Task 031 | 2025-05-10 | 2025-07-24 | 2025-05-12 | 2025-06-30 | 49 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-032 | Task 032 | 2025-10-20 | 2025-11-20 | 2025-10-21 | 2025-11-06 | 16 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-033 | Task 033 | 2025-10-27 | 2025-10-31 | 2025-10-28 | 2025-11-13 | 16 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-034 | Task 034 | 2025-10-20 | 2025-11-06 | 2025-10-19 | 2025-11-10 | 22 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | L | 0 |  | Update_010
Gamma | TSK-035 | Task 035 | 2025-03-16 | 2025-04-06 | 2025-03-15 | 2025-04-05 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-036 | Task 036 | 2025-01-22 | 2025-04-19 | 2025-01-21 | 2025-03-08 | 46 | TRUE | 41 | 89.1 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 8 | Delayed by 41 days (+5 points); Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_010
Gamma | TSK-037 | Task 037 | 2025-04-11 | 2025-07-27 | 2025-04-11 | 2025-05-14 | 33 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-038 | Task 038 | 2025-05-11 | 2025-06-28 | 2025-05-14 | 2025-06-16 | 33 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-039 | Task 039 | 2025-06-23 | 2025-08-27 | 2025-06-21 | 2025-08-15 | 55 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-040 | Task 040 | 2025-08-16 |  | 2025-08-17 | 2025-09-23 | 37 | FALSE | 0 | 0 |  | Started | FALSE | FALSE | TRUE | Low | 0 |  | Update_010
Gamma | TSK-041 | Task 041 | 2025-01-07 | 2025-03-07 | 2025-01-09 | 2025-02-08 | 30 | TRUE | 26 | 86.7 | 1 | Complete | FALSE | TRUE | FALSE | High | 7 | Delayed by 26 days (+3 points); Risk Level: High (+2 points); On Critical Path (+2 points) | Update_010
Gamma | TSK-042 | Task 042 | 2025-09-22 | 2025-11-11 | 2025-09-19 | 2025-11-10 | 52 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-043 | Task 043 | 2025-01-11 | 2025-02-17 | 2025-01-09 | 2025-02-10 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-044 | Task 044 | 2025-10-20 | 2026-01-22 | 2025-10-17 | 2025-12-15 | 59 | TRUE | 37 | 62.7 | 100% | Complete | TRUE | FALSE | FALSE |  | 5 | Delayed by 37 days (+4 points); Milestone Task (+1 point) | Update_010
Gamma | TSK-045 | Task 045 | 2025-01-04 | 2025-03-01 | 2025-01-07 | 2025-02-16 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-046 | Task 046 | 2025-04-14 | 2025-06-23 | 2025-04-11 | 2025-05-24 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Gamma | TSK-047 | Task 047 | 2025-07-26 | 2025-08-27 | 2025-07-23 | 2025-09-01 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-048 | Task 048 | 2024-11-28 | 2025-03-13 | 2024-11-25 | 2025-01-15 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-049 | Task 049 | 2025-06-21 | 2025-10-04 | 2025-06-22 | 2025-08-04 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-050 | Task 050 | 2024-12-06 | 2024-12-24 | 2024-12-03 | 2024-12-26 | 23 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-051 | Task 051 | 2025-08-20 | 2025-10-18 | 2025-08-22 | 2025-09-25 | 34 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-052 | Task 052 | 2025-10-01 | 2026-02-10 | 2025-10-04 | 2025-11-28 | 55 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-053 | Task 053 | 2025-09-08 | 2025-11-24 | 2025-09-05 | 2025-11-03 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-054 | Task 054 | 2025-10-06 | 2026-01-06 | 2025-10-09 | 2025-11-14 | 36 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-055 | Task 055 | 2025-07-04 | 2025-10-03 | 2025-07-01 | 2025-08-29 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-056 | Task 056 | 2025-04-24 | 2025-05-31 | 2025-04-21 | 2025-05-15 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Gamma | TSK-057 | Task 057 | 2025-10-26 | 2025-12-12 | 2025-10-28 | 2025-11-11 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-058 | Task 058 | 2024-11-21 | 2025-01-25 | 2024-11-19 | 2024-12-12 | 23 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-059 | Task 059 | 2025-04-07 | 2025-06-18 | 2025-04-04 | 2025-05-25 | 51 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-060 | Task 060 | 2025-04-06 | 2025-05-31 | 2025-04-06 | 2025-05-16 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-061 | Task 061 | 2025-05-18 | 2025-05-24 | 2025-05-18 | 2025-06-26 | 39 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-062 | Task 062 | 2025-10-05 | 2025-11-30 | 2025-10-03 | 2025-10-22 | 19 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | H | 0 |  | Update_010
Gamma | TSK-063 | Task 063 | 2024-12-07 | 2025-02-22 | 2024-12-09 | 2025-02-06 | 59 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-064 | Task 064 | 2025-08-02 | 2025-08-30 | 2025-07-30 | 2025-08-09 | 10 | TRUE | 20 | 200 | 100% | Complete | TRUE | TRUE | FALSE | H | 7 | Delayed by 20 days (+2 points); Risk Level: H (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_010
Gamma | TSK-065 | Task 065 | 2024-11-06 | 2024-12-23 | 2024-11-05 | 2024-12-22 | 47 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-066 | Task 066 | 2024-11-23 | 2024-12-29 | 2024-11-23 | 2025-01-03 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Gamma | TSK-067 | Task 067 | 2025-05-13 | 2025-08-27 | 2025-05-14 | 2025-06-30 | 47 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Gamma | TSK-068 | Task 068 | 2025-06-09 | 2025-08-08 | 2025-06-08 | 2025-07-09 | 31 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-069 | Task 069 | 2025-01-26 | 2025-04-04 | 2025-01-25 | 2025-02-26 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Gamma | TSK-070 | Task 070 | 2025-09-26 | 2025-12-31 | 2025-09-27 | 2025-11-11 | 45 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | L | 0 |  | Update_010
Gamma | TSK-071 | Task 071 | 2025-06-10 | 2025-09-14 | 2025-06-13 | 2025-07-23 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-072 | Task 072 | 2025-07-17 | 2025-07-28 | 2025-07-20 | 2025-07-31 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Gamma | TSK-073 | Task 073 | 2025-06-22 | 2025-08-19 | 2025-06-23 | 2025-07-22 | 29 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_010
Gamma | TSK-074 | Task 074 | 2024-11-18 | 2024-12-31 | 2024-11-18 | 2024-11-29 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Gamma | TSK-075 | Task 075 | 2025-04-17 | 2025-07-07 | 2025-04-15 | 2025-05-17 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010