## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Slippages | TSK-001 | Task 001 | 2025-05-21 | 2025-06-20 | 2025-05-22 | 2025-06-05 | 14 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Slippages | TSK-002 | Task 002 | 2025-03-02 | 2025-03-10 | 2025-03-04 | 2025-04-03 | 30 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-003 | Task 003 | 2025-06-13 | 2025-09-09 | 2025-06-12 | 2025-07-23 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-004 | Task 004 | 2025-04-27 | 2025-08-20 | 2025-04-28 | 2025-06-07 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Slippages | TSK-005 | Task 005 | 2025-08-31 | 2025-12-12 | 2025-09-02 | 2025-10-17 | 45 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-006 | Task 006 | 2025-07-13 | 2025-11-13 | 2025-07-16 | 2025-08-10 | 25 | TRUE | 94 | 376 | Complete | Complete | TRUE | FALSE | FALSE | Medium | 7 | Delayed by 94 days (+5 points); Risk Level: Medium (+1 points); Milestone Task (+1 point) | Update_010
Slippages | TSK-007 | Task 007 | 2025-03-14 | 2025-05-04 | 2025-03-17 | 2025-04-22 | 36 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Slippages | TSK-008 | Task 008 | 2024-12-10 | 2025-02-05 | 2024-12-10 | 2025-01-14 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-009 | Task 009 | 2025-10-03 | 2026-02-27 | 2025-10-02 | 2025-11-09 | 38 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-010 | Task 010 | 2025-05-02 | 2025-07-20 | 2025-05-01 | 2025-06-28 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-011 | Task 011 | 2025-08-18 | 2025-11-14 | 2025-08-21 | 2025-10-03 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-012 | Task 012 | 2025-03-16 | 2025-06-29 | 2025-03-16 | 2025-04-01 | 16 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Slippages | TSK-013 | Task 013 | 2025-10-14 | 2026-01-19 | 2025-10-13 | 2025-12-07 | 55 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | L | 0 |  | Update_010
Slippages | TSK-014 | Task 014 | 2025-03-01 | 2025-03-14 | 2025-03-01 | 2025-03-26 | 25 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-015 | Task 015 | 2025-07-11 | 2025-09-16 | 2025-07-08 | 2025-09-02 | 56 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Slippages | TSK-016 | Task 016 | 2025-04-16 | 2025-07-12 | 2025-04-16 | 2025-05-25 | 39 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-017 | Task 017 | 2024-11-06 | 2025-02-17 | 2024-11-06 | 2024-12-10 | 34 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-018 | Task 018 | 2025-06-01 | 2025-08-21 | 2025-05-29 | 2025-06-22 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-019 | Task 019 | 2025-06-06 | 2025-08-09 | 2025-06-08 | 2025-07-08 | 30 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-020 | Task 020 | 2025-01-29 | 2025-03-10 | 2025-01-27 | 2025-02-14 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-021 | Task 021 | 2025-07-23 | 2025-12-07 | 2025-07-20 | 2025-09-05 | 47 | TRUE | 92 | 195.7 | Complete | Complete | FALSE | FALSE | FALSE | Medium | 6 | Delayed by 92 days (+5 points); Risk Level: Medium (+1 points) | Update_010
Slippages | TSK-022 | Task 022 | 2025-04-12 | 2025-06-04 | 2025-04-09 | 2025-06-03 | 55 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-023 | Task 023 | 2025-04-02 | 2025-06-21 | 2025-03-31 | 2025-05-29 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-024 | Task 024 | 2025-05-08 | 2025-07-12 | 2025-05-08 | 2025-06-09 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-025 | Task 025 | 2025-01-08 | 2025-03-19 | 2025-01-09 | 2025-03-10 | 60 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Slippages | TSK-026 | Task 026 | 2025-10-13 | 2025-12-06 | 2025-10-15 | 2025-10-25 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-027 | Task 027 | 2025-07-13 | 2025-09-06 | 2025-07-14 | 2025-08-13 | 30 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-028 | Task 028 | 2025-01-14 | 2025-03-28 | 2025-01-12 | 2025-03-12 | 59 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-029 | Task 029 | 2025-04-29 | 2025-06-12 | 2025-05-02 | 2025-05-29 | 27 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-030 | Task 030 | 2025-03-10 | 2025-04-26 | 2025-03-08 | 2025-04-02 | 25 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-031 | Task 031 | 2025-02-07 | 2025-04-25 | 2025-02-05 | 2025-03-06 | 29 | TRUE | 49 | 169 | 100% | Complete | FALSE | FALSE | FALSE |  | 5 | Delayed by 49 days (+5 points) | Update_010
Slippages | TSK-032 | Task 032 | 2025-03-10 | 2025-03-15 | 2025-03-10 | 2025-04-07 | 28 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-033 | Task 033 | 2025-05-01 | 2025-08-10 | 2025-05-01 | 2025-06-22 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Slippages | TSK-034 | Task 034 | 2025-08-05 | 2025-09-13 | 2025-08-04 | 2025-08-21 | 17 | TRUE | 22 | 129.4 | Complete | Complete | FALSE | FALSE | FALSE | H | 5 | Delayed by 22 days (+3 points); Risk Level: H (+2 points) | Update_010
Slippages | TSK-035 | Task 035 | 2025-01-05 | 2025-03-09 | 2025-01-04 | 2025-02-18 | 45 | TRUE | 18 | 40 | Complete | Complete | FALSE | TRUE | FALSE |  | 4 | Delayed by 18 days (+2 points); On Critical Path (+2 points) | Update_010
Slippages | TSK-036 | Task 036 | 2025-01-15 | 2025-03-05 | 2025-01-18 | 2025-03-02 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-037 | Task 037 | 2025-04-02 | 2025-07-03 | 2025-03-30 | 2025-05-21 | 52 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_010
Slippages | TSK-038 | Task 038 | 2025-07-09 | 2025-09-28 | 2025-07-12 | 2025-08-16 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-039 | Task 039 | 2025-05-25 | 2025-07-20 | 2025-05-26 | 2025-07-08 | 43 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-040 | Task 040 | 2025-06-05 | 2025-06-22 | 2025-06-06 | 2025-06-18 | 12 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-041 | Task 041 | 2025-04-07 | 2025-06-19 | 2025-04-07 | 2025-05-14 | 37 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-042 | Task 042 | 2025-10-17 | 2026-02-08 | 2025-10-14 | 2025-12-05 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-043 | Task 043 | 2025-02-15 | 2025-03-22 | 2025-02-15 | 2025-03-17 | 30 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-044 | Task 044 | 2025-10-30 | 2026-01-04 | 2025-10-30 | 2025-12-08 | 39 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-045 | Task 045 | 2025-06-03 | 2025-08-22 | 2025-06-05 | 2025-06-17 | 12 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-046 | Task 046 | 2025-05-31 | 2025-10-14 | 2025-06-02 | 2025-07-23 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-047 | Task 047 | 2025-02-26 | 2025-05-13 | 2025-02-25 | 2025-04-12 | 46 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-048 | Task 048 | 2025-10-16 | 2025-12-03 | 2025-10-14 | 2025-11-10 | 27 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-049 | Task 049 | 2025-03-12 | 2025-05-31 | 2025-03-10 | 2025-05-06 | 57 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_010
Slippages | TSK-050 | Task 050 | 2024-11-19 | 2025-02-01 | 2024-11-18 | 2025-01-07 | 50 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-051 | Task 051 | 2024-12-30 | 2025-03-19 | 2024-12-31 | 2025-02-13 | 44 | TRUE | 33 | 75 | 100% | Complete | FALSE | FALSE | FALSE | Low | 4 | Delayed by 33 days (+4 points) | Update_010
Slippages | TSK-052 | Task 052 | 2024-12-17 | 2025-02-21 | 2024-12-15 | 2025-01-02 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-053 | Task 053 | 2025-07-28 | 2025-10-21 | 2025-07-25 | 2025-09-05 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Slippages | TSK-054 | Task 054 | 2025-02-25 | 2025-05-11 | 2025-02-27 | 2025-04-10 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-055 | Task 055 | 2025-10-16 | 2026-02-04 | 2025-10-16 | 2025-12-04 | 49 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Slippages | TSK-056 | Task 056 | 2025-04-17 | 2025-05-19 | 2025-04-14 | 2025-04-30 | 16 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-057 | Task 057 | 2025-01-23 | 2025-04-04 | 2025-01-25 | 2025-02-06 | 12 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-058 | Task 058 | 2025-04-26 | 2025-07-08 | 2025-04-24 | 2025-05-24 | 30 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-059 | Task 059 | 2025-06-05 | 2025-09-23 | 2025-06-03 | 2025-07-20 | 47 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | High | 0 |  | Update_010
Slippages | TSK-060 | Task 060 | 2025-08-11 | 2025-09-20 | 2025-08-08 | 2025-08-24 | 16 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Slippages | TSK-061 | Task 061 | 2025-03-05 | 2025-05-22 | 2025-03-04 | 2025-05-01 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Slippages | TSK-062 | Task 062 | 2025-07-15 | 2025-10-19 | 2025-07-16 | 2025-09-07 | 53 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Slippages | TSK-063 | Task 063 | 2025-01-11 | 2025-03-26 | 2025-01-13 | 2025-02-10 | 28 | TRUE | 43 | 153.6 | 100% | Complete | FALSE | TRUE | FALSE |  | 7 | Delayed by 43 days (+5 points); On Critical Path (+2 points) | Update_010
Slippages | TSK-064 | Task 064 | 2025-04-13 | 2025-06-30 | 2025-04-16 | 2025-06-03 | 48 | TRUE | 26 | 54.2 | 100% | Complete | FALSE | FALSE | FALSE | H | 5 | Delayed by 26 days (+3 points); Risk Level: H (+2 points) | Update_010
Slippages | TSK-065 | Task 065 | 2025-05-03 | 2025-07-14 | 2025-05-01 | 2025-06-28 | 58 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | L | 0 |  | Update_010
Slippages | TSK-066 | Task 066 | 2025-02-06 | 2025-05-08 | 2025-02-04 | 2025-03-14 | 38 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Slippages | TSK-067 | Task 067 | 2025-09-12 | 2025-11-04 | 2025-09-11 | 2025-11-01 | 51 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-068 | Task 068 | 2025-10-22 | 2025-11-26 | 2025-10-24 | 2025-11-27 | 34 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | H | 0 |  | Update_010
Slippages | TSK-069 | Task 069 | 2025-01-26 | 2025-04-08 | 2025-01-28 | 2025-03-08 | 39 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-070 | Task 070 | 2025-05-05 | 2025-07-29 | 2025-05-06 | 2025-06-30 | 55 | TRUE | 28 | 50.9 | Complete | Complete | TRUE | FALSE | FALSE |  | 4 | Delayed by 28 days (+3 points); Milestone Task (+1 point) | Update_010
Slippages | TSK-071 | Task 071 | 2025-09-22 | 2025-11-26 | 2025-09-22 | 2025-11-02 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_010
Slippages | TSK-072 | Task 072 | 2025-10-28 | 2025-12-30 | 2025-10-30 | 2025-12-12 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Slippages | TSK-073 | Task 073 | 2025-06-26 | 2025-09-22 | 2025-06-29 | 2025-07-20 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Slippages | TSK-074 | Task 074 | 2025-04-07 | 2025-07-21 | 2025-04-06 | 2025-05-21 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Slippages | TSK-075 | Task 075 | 2025-06-21 | 2025-09-07 | 2025-06-18 | 2025-08-02 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010