## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Beta | TSK-001 | Task 001 | 2025-01-08 | 2025-02-22 | 2025-01-06 | 2025-01-29 | 23 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_005
Beta | TSK-002 | Task 002 | 2025-02-20 | 2025-02-26 | 2025-02-18 | 2025-04-19 | 60 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-003 | Task 003 | 2025-04-28 | 2025-09-01 | 2025-04-30 | 2025-06-14 | 45 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-004 | Task 004 | 2025-07-18 | 2025-09-29 | 2025-07-21 | 2025-09-05 | 46 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-005 | Task 005 | 2025-06-07 | 2025-09-09 | 2025-06-04 | 2025-07-16 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_005
Beta | TSK-006 | Task 006 | 2025-09-04 | 2025-11-25 | 2025-09-03 | 2025-11-02 | 60 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-007 | Task 007 | 2025-06-01 | 2025-07-10 | 2025-05-29 | 2025-06-15 | 17 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_005
Beta | TSK-008 | Task 008 | 2025-02-11 | 2025-04-29 | 2025-02-13 | 2025-03-07 | 22 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-009 | Task 009 | 2025-09-08 | 2025-10-04 | 2025-09-10 | 2025-10-03 | 23 | TRUE | 1 | 4.3 | 100% | Complete | TRUE | FALSE | FALSE | L | 2 | Delayed by 1 days (+1 points); Milestone Task (+1 point) | Update_005
Beta | TSK-010 | Task 010 | 2025-10-11 | 2026-01-07 | 2025-10-13 | 2025-11-18 | 36 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-011 | Task 011 | 2024-11-20 | 2025-01-07 | 2024-11-17 | 2024-12-13 | 26 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-012 | Task 012 | 2025-05-13 | 2025-07-12 | 2025-05-15 | 2025-06-23 | 39 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | High | 0 |  | Update_005
Beta | TSK-013 | Task 013 | 2025-10-26 | 2025-11-28 | 2025-10-28 | 2025-11-13 | 16 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-014 | Task 014 | 2024-12-10 | 2025-03-07 | 2024-12-09 | 2025-02-06 | 59 | TRUE | 29 | 49.2 | Complete | Complete | FALSE | TRUE | FALSE | L | 5 | Delayed by 29 days (+3 points); On Critical Path (+2 points) | Update_005
Beta | TSK-015 | Task 015 | 2025-07-12 | 2025-10-01 | 2025-07-10 | 2025-07-21 | 11 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_005
Beta | TSK-016 | Task 016 | 2025-10-25 | 2025-11-04 | 2025-10-25 | 2025-11-15 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-017 | Task 017 | 2024-12-04 | 2025-01-07 | 2024-12-04 | 2024-12-15 | 11 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-018 | Task 018 | 2025-02-11 |  | 2025-02-11 | 2025-02-22 | 11 | FALSE | 0 | 0 | 77% | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_005
Beta | TSK-019 | Task 019 | 2025-04-06 | 2025-07-28 | 2025-04-06 | 2025-05-26 | 50 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-020 | Task 020 | 2025-01-15 |  | 2025-01-17 | 2025-02-18 | 32 | FALSE | 0 | 0 | 0.25413 | Started | FALSE | FALSE | TRUE |  | 0 |  | Update_005
Beta | TSK-021 | Task 021 | 2024-12-05 | 2025-02-14 | 2024-12-03 | 2025-01-21 | 49 | TRUE | 24 | 49 | Complete | Complete | FALSE | TRUE | FALSE | Low | 5 | Delayed by 24 days (+3 points); On Critical Path (+2 points) | Update_005
Beta | TSK-022 | Task 022 | 2025-03-08 | 2025-06-17 | 2025-03-11 | 2025-04-30 | 50 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_005
Beta | TSK-023 | Task 023 | 2025-10-21 | 2025-12-28 | 2025-10-22 | 2025-11-13 | 22 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-024 | Task 024 | 2025-02-15 | 2025-06-16 | 2025-02-13 | 2025-04-01 | 47 | TRUE | 75 | 159.6 | Complete | Complete | FALSE | FALSE | FALSE | High | 7 | Delayed by 75 days (+5 points); Risk Level: High (+2 points) | Update_005
Beta | TSK-025 | Task 025 | 2025-06-28 |  | 2025-06-25 | 2025-07-18 | 23 | FALSE | 0 | 0 |  | In Progress | TRUE | FALSE | TRUE |  | 1 | Milestone Task (+1 point) | Update_005
Beta | TSK-026 | Task 026 | 2025-07-08 | 2025-07-22 | 2025-07-10 | 2025-07-20 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-027 | Task 027 | 2024-12-10 | 2025-03-11 | 2024-12-11 | 2025-01-20 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_005
Beta | TSK-028 | Task 028 | 2025-06-08 | 2025-07-05 | 2025-06-11 | 2025-07-02 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-029 | Task 029 | 2025-02-05 | 2025-05-29 | 2025-02-04 | 2025-04-02 | 57 | TRUE | 56 | 98.2 | Complete | Complete | FALSE | FALSE | FALSE | High | 7 | Delayed by 56 days (+5 points); Risk Level: High (+2 points) | Update_005
Beta | TSK-030 | Task 030 | 2025-06-01 | 2025-08-08 | 2025-05-29 | 2025-07-25 | 57 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_005
Beta | TSK-031 | Task 031 | 2025-10-16 | 2025-12-21 | 2025-10-14 | 2025-11-06 | 23 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-032 | Task 032 | 2025-10-10 | 2025-11-30 | 2025-10-11 | 2025-11-15 | 35 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-033 | Task 033 | 2025-02-18 | 2025-06-18 | 2025-02-20 | 2025-03-30 | 38 | TRUE | 79 | 207.9 | 100% | Complete | FALSE | FALSE | FALSE | High | 7 | Delayed by 79 days (+5 points); Risk Level: High (+2 points) | Update_005
Beta | TSK-034 | Task 034 | 2025-04-26 |  | 2025-04-23 | 2025-05-20 | 27 | FALSE | 0 | 0 | 73% | In Progress | FALSE | TRUE | TRUE |  | 2 | On Critical Path (+2 points) | Update_005
Beta | TSK-035 | Task 035 | 2025-03-29 | 2025-04-30 | 2025-03-31 | 2025-04-15 | 15 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-036 | Task 036 | 2024-11-24 | 2025-01-14 | 2024-11-25 | 2024-12-05 | 10 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-037 | Task 037 | 2024-11-20 |  | 2024-11-23 | 2025-01-12 | 50 | FALSE | 0 | 0 | 33% | Started | FALSE | TRUE | TRUE | Medium | 3 | Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_005
Beta | TSK-038 | Task 038 | 2024-12-08 | 2025-01-07 | 2024-12-10 | 2025-01-13 | 34 | FALSE | -7 | -20.6 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-039 | Task 039 | 2025-01-16 | 2025-04-12 | 2025-01-17 | 2025-02-14 | 28 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-040 | Task 040 | 2024-11-27 | 2025-01-26 | 2024-11-27 | 2024-12-08 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-041 | Task 041 | 2025-04-03 | 2025-06-02 | 2025-04-05 | 2025-04-29 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-042 | Task 042 | 2025-02-09 | 2025-04-08 | 2025-02-09 | 2025-02-25 | 16 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-043 | Task 043 | 2025-09-23 |  | 2025-09-23 | 2025-11-22 | 60 | FALSE | 0 | 0 | 23% | Started | FALSE | FALSE | TRUE | H | 2 | Risk Level: H (+2 points) | Update_005
Beta | TSK-044 | Task 044 | 2025-10-18 | 2025-11-02 | 2025-10-15 | 2025-12-03 | 49 | FALSE | -32 | -65.3 | 100% | Complete | TRUE | FALSE | FALSE | H | 3 | Risk Level: H (+2 points); Milestone Task (+1 point) | Update_005
Beta | TSK-045 | Task 045 | 2025-02-01 | 2025-03-26 | 2025-01-30 | 2025-02-09 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_005
Beta | TSK-046 | Task 046 | 2025-08-01 | 2025-09-27 | 2025-08-02 | 2025-09-12 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_005
Beta | TSK-047 | Task 047 | 2024-11-23 | 2025-02-22 | 2024-11-22 | 2025-01-10 | 49 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-048 | Task 048 | 2025-03-21 | 2025-05-31 | 2025-03-21 | 2025-04-23 | 33 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-049 | Task 049 | 2025-10-11 | 2025-11-21 | 2025-10-13 | 2025-11-25 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_005
Beta | TSK-050 | Task 050 | 2025-03-07 | 2025-05-18 | 2025-03-06 | 2025-04-16 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-051 | Task 051 | 2025-01-04 | 2025-03-31 | 2025-01-03 | 2025-02-07 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-052 | Task 052 | 2025-04-22 | 2025-08-16 | 2025-04-24 | 2025-06-15 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_005
Beta | TSK-053 | Task 053 | 2025-01-12 | 2025-02-11 | 2025-01-11 | 2025-01-22 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-054 | Task 054 | 2025-03-14 | 2025-05-14 | 2025-03-16 | 2025-04-14 | 29 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_005
Beta | TSK-055 | Task 055 | 2025-01-31 | 2025-04-15 | 2025-02-01 | 2025-03-05 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-056 | Task 056 | 2025-06-25 | 2025-08-19 | 2025-06-22 | 2025-07-13 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_005
Beta | TSK-057 | Task 057 | 2025-03-18 | 2025-03-28 | 2025-03-21 | 2025-04-02 | 12 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-058 | Task 058 | 2025-10-25 | 2026-01-24 | 2025-10-28 | 2025-11-27 | 30 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-059 | Task 059 | 2025-03-18 | 2025-06-13 | 2025-03-16 | 2025-04-25 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-060 | Task 060 | 2024-12-01 | 2025-01-17 | 2024-12-01 | 2024-12-24 | 23 | TRUE | 23 | 100 | Complete | Complete | TRUE | TRUE | FALSE | H | 8 | Delayed by 23 days (+3 points); Risk Level: H (+2 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_005
Beta | TSK-061 | Task 061 | 2025-06-08 | 2025-08-23 | 2025-06-09 | 2025-07-02 | 23 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_005
Beta | TSK-062 | Task 062 | 2025-01-05 |  | 2025-01-02 | 2025-02-18 | 47 | FALSE | 0 | 0 |  | In Progress | FALSE | FALSE | TRUE | High | 2 | Risk Level: High (+2 points) | Update_005
Beta | TSK-063 | Task 063 | 2025-05-30 | 2025-08-07 | 2025-05-27 | 2025-06-16 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_005
Beta | TSK-064 | Task 064 | 2025-06-04 | 2025-08-10 | 2025-06-01 | 2025-06-25 | 24 | TRUE | 45 | 187.5 | 100% | Complete | FALSE | TRUE | FALSE | L | 7 | Delayed by 45 days (+5 points); On Critical Path (+2 points) | Update_005
Beta | TSK-065 | Task 065 | 2025-01-09 | 2025-03-21 | 2025-01-06 | 2025-02-15 | 40 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_005
Beta | TSK-066 | Task 066 | 2025-10-30 | 2026-01-27 | 2025-10-29 | 2025-12-04 | 36 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-067 | Task 067 | 2025-10-27 | 2025-12-27 | 2025-10-25 | 2025-11-04 | 10 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-068 | Task 068 | 2025-05-11 | 2025-07-07 | 2025-05-10 | 2025-06-05 | 26 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_005
Beta | TSK-069 | Task 069 | 2025-08-15 | 2025-10-17 | 2025-08-13 | 2025-08-24 | 11 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_005
Beta | TSK-070 | Task 070 | 2025-10-08 | 2025-12-11 | 2025-10-05 | 2025-11-09 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-071 | Task 071 | 2025-02-10 | 2025-04-26 | 2025-02-09 | 2025-04-02 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_005
Beta | TSK-072 | Task 072 | 2025-01-02 |  | 2025-01-05 | 2025-01-26 | 21 | FALSE | 0 | 0 | 26% | In Progress | FALSE | FALSE | TRUE | Medium | 1 | Risk Level: Medium (+1 points) | Update_005
Beta | TSK-073 | Task 073 | 2024-11-17 | 2025-03-02 | 2024-11-14 | 2025-01-03 | 50 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_005
Beta | TSK-074 | Task 074 | 2025-05-09 | 2025-07-12 | 2025-05-08 | 2025-07-02 | 55 | TRUE | 9 | 16.4 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 4 | Delayed by 9 days (+1 points); Risk Level: Medium (+1 points); On Critical Path (+2 points) | Update_005
Beta | TSK-075 | Task 075 | 2025-04-19 | 2025-07-12 | 2025-04-16 | 2025-05-14 | 28 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | L | 0 |  | Update_005