## Sheet1
project_name | task_id | task_name | actual_start | actual_finish | baseline_start | baseline_end | baseline_duration | is_delayed | delay_days | delay_percentage | percent_complete | status | is_milestone | is_critical | is_active | risk_flag | severity_score | severity_factors | update_phase
Updates | TSK-001 | Task 001 | 2025-07-09 | 2025-08-24 | 2025-07-11 | 2025-07-29 | 18 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Updates | TSK-002 | Task 002 | 2025-05-04 | 2025-07-14 | 2025-05-07 | 2025-06-19 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Updates | TSK-003 | Task 003 | 2025-04-27 | 2025-05-27 | 2025-04-30 | 2025-05-10 | 10 | TRUE | 16 | 160 | 100% | Complete | FALSE | TRUE | FALSE | High | 6 | Delayed by 16 days (+2 points); Risk Level: High (+2 points); On Critical Path (+2 points) | Update_010
Updates | TSK-004 | Task 004 | 2025-05-25 | 2025-09-10 | 2025-05-24 | 2025-07-20 | 57 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-005 | Task 005 | 2025-01-20 | 2025-04-24 | 2025-01-17 | 2025-02-28 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-006 | Task 006 | 2024-11-25 | 2024-12-12 | 2024-11-26 | 2024-12-09 | 13 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Updates | TSK-007 | Task 007 | 2025-02-09 | 2025-04-18 | 2025-02-08 | 2025-03-22 | 42 | TRUE | 26 | 61.9 | 100% | Complete | FALSE | FALSE | FALSE | H | 5 | Delayed by 26 days (+3 points); Risk Level: H (+2 points) | Update_010
Updates | TSK-008 | Task 008 | 2025-01-28 | 2025-03-03 | 2025-01-28 | 2025-03-08 | 39 | FALSE | -6 | -15.4 | Complete | Complete | FALSE | TRUE | FALSE | High | 4 | Risk Level: High (+2 points); On Critical Path (+2 points) | Update_010
Updates | TSK-009 | Task 009 | 2025-04-08 | 2025-05-16 | 2025-04-07 | 2025-04-29 | 22 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Updates | TSK-010 | Task 010 | 2025-04-23 | 2025-09-05 | 2025-04-24 | 2025-06-12 | 49 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Updates | TSK-011 | Task 011 | 2025-10-10 | 2025-11-18 | 2025-10-07 | 2025-10-21 | 14 | TRUE | 27 | 192.9 | Complete | Complete | TRUE | TRUE | FALSE | L | 6 | Delayed by 27 days (+3 points); On Critical Path (+2 points); Milestone Task (+1 point) | Update_010
Updates | TSK-012 | Task 012 | 2025-03-09 | 2025-04-21 | 2025-03-12 | 2025-04-16 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-013 | Task 013 | 2025-04-17 | 2025-07-09 | 2025-04-14 | 2025-06-08 | 55 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-014 | Task 014 | 2024-12-12 | 2025-03-19 | 2024-12-14 | 2025-02-10 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Updates | TSK-015 | Task 015 | 2025-05-12 | 2025-08-04 | 2025-05-15 | 2025-06-05 | 21 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-016 | Task 016 | 2025-06-16 | 2025-10-03 | 2025-06-17 | 2025-07-16 | 29 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Low | 0 |  | Update_010
Updates | TSK-017 | Task 017 | 2025-02-17 | 2025-03-28 | 2025-02-15 | 2025-03-03 | 16 | TRUE | 24 | 150 | 100% | Complete | FALSE | FALSE | FALSE | H | 5 | Delayed by 24 days (+3 points); Risk Level: H (+2 points) | Update_010
Updates | TSK-018 | Task 018 | 2024-12-31 | 2025-02-11 | 2024-12-31 | 2025-01-19 | 19 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-019 | Task 019 | 2025-07-17 | 2025-10-02 | 2025-07-18 | 2025-08-14 | 27 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Updates | TSK-020 | Task 020 | 2025-04-10 | 2025-07-08 | 2025-04-07 | 2025-05-24 | 47 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Updates | TSK-021 | Task 021 | 2024-12-21 | 2025-02-25 | 2024-12-23 | 2025-02-04 | 43 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-022 | Task 022 | 2025-08-22 | 2025-09-21 | 2025-08-21 | 2025-09-01 | 11 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-023 | Task 023 | 2025-01-11 | 2025-01-30 | 2025-01-14 | 2025-01-30 | 16 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-024 | Task 024 | 2025-02-11 | 2025-06-19 | 2025-02-14 | 2025-03-27 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-025 | Task 025 | 2025-05-06 | 2025-08-02 | 2025-05-07 | 2025-06-21 | 45 | TRUE | 41 | 91.1 | 100% | Complete | TRUE | FALSE | FALSE | High | 8 | Delayed by 41 days (+5 points); Risk Level: High (+2 points); Milestone Task (+1 point) | Update_010
Updates | TSK-026 | Task 026 | 2025-06-22 | 2025-08-14 | 2025-06-19 | 2025-07-25 | 36 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-027 | Task 027 | 2025-08-29 | 2025-11-19 | 2025-08-29 | 2025-10-27 | 59 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-028 | Task 028 | 2025-07-25 | 2025-09-03 | 2025-07-22 | 2025-08-11 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-029 | Task 029 | 2025-03-22 | 2025-04-25 | 2025-03-22 | 2025-04-13 | 22 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-030 | Task 030 | 2024-12-02 | 2024-12-20 | 2024-12-04 | 2024-12-17 | 13 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-031 | Task 031 | 2025-05-26 | 2025-08-05 | 2025-05-26 | 2025-07-01 | 36 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-032 | Task 032 | 2025-04-12 | 2025-05-23 | 2025-04-15 | 2025-05-17 | 32 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | H | 0 |  | Update_010
Updates | TSK-033 | Task 033 | 2025-06-03 | 2025-07-22 | 2025-06-03 | 2025-07-08 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Updates | TSK-034 | Task 034 | 2025-05-30 | 2025-07-13 | 2025-05-30 | 2025-07-16 | 47 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Low | 0 |  | Update_010
Updates | TSK-035 | Task 035 | 2024-12-20 | 2025-04-21 | 2024-12-20 | 2025-02-02 | 44 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-036 | Task 036 | 2025-08-14 | 2025-10-01 | 2025-08-12 | 2025-08-29 | 17 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE | High | 0 |  | Update_010
Updates | TSK-037 | Task 037 | 2025-03-08 | 2025-04-16 | 2025-03-09 | 2025-04-06 | 28 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-038 | Task 038 | 2025-01-05 | 2025-03-17 | 2025-01-08 | 2025-03-07 | 58 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-039 | Task 039 | 2025-02-03 | 2025-04-23 | 2025-02-04 | 2025-02-24 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-040 | Task 040 | 2025-01-19 | 2025-04-02 | 2025-01-18 | 2025-03-12 | 53 | TRUE | 20 | 37.7 | 100% | Complete | FALSE | FALSE | FALSE | High | 4 | Delayed by 20 days (+2 points); Risk Level: High (+2 points) | Update_010
Updates | TSK-041 | Task 041 | 2025-02-28 | 2025-05-16 | 2025-02-26 | 2025-03-22 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Updates | TSK-042 | Task 042 | 2025-02-07 | 2025-02-21 | 2025-02-04 | 2025-02-24 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Updates | TSK-043 | Task 043 | 2025-07-04 | 2025-09-15 | 2025-07-04 | 2025-08-25 | 52 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-044 | Task 044 | 2025-05-25 | 2025-08-21 | 2025-05-23 | 2025-06-21 | 29 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-045 | Task 045 | 2025-05-03 | 2025-05-21 | 2025-05-04 | 2025-05-23 | 19 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-046 | Task 046 | 2025-10-16 | 2025-12-24 | 2025-10-15 | 2025-11-29 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-047 | Task 047 | 2025-04-12 | 2025-06-12 | 2025-04-12 | 2025-05-30 | 48 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-048 | Task 048 | 2025-04-19 | 2025-08-15 | 2025-04-20 | 2025-06-04 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-049 | Task 049 | 2025-05-03 | 2025-06-18 | 2025-05-05 | 2025-05-21 | 16 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_010
Updates | TSK-050 | Task 050 | 2024-11-25 | 2024-12-12 | 2024-11-22 | 2024-12-16 | 24 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | L | 0 |  | Update_010
Updates | TSK-051 | Task 051 | 2025-01-30 | 2025-04-22 | 2025-01-28 | 2025-03-25 | 56 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Updates | TSK-052 | Task 052 | 2025-09-09 | 2025-10-15 | 2025-09-06 | 2025-10-12 | 36 | FALSE | 0 | 0 | 100% | Complete | TRUE | TRUE | FALSE |  | 0 |  | Update_010
Updates | TSK-053 | Task 053 | 2024-11-07 | 2025-01-30 | 2024-11-07 | 2025-01-06 | 60 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-054 | Task 054 | 2025-03-24 | 2025-04-30 | 2025-03-21 | 2025-05-05 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | High | 0 |  | Update_010
Updates | TSK-055 | Task 055 | 2024-12-17 | 2025-01-23 | 2024-12-15 | 2025-01-22 | 38 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-056 | Task 056 | 2025-07-14 | 2025-09-27 | 2025-07-13 | 2025-08-20 | 38 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-057 | Task 057 | 2025-05-03 | 2025-08-21 | 2025-04-30 | 2025-06-24 | 55 | TRUE | 57 | 103.6 | 100% | Complete | FALSE | FALSE | FALSE | H | 7 | Delayed by 57 days (+5 points); Risk Level: H (+2 points) | Update_010
Updates | TSK-058 | Task 058 | 2025-02-10 | 2025-05-01 | 2025-02-12 | 2025-04-13 | 60 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-059 | Task 059 | 2025-04-19 | 2025-05-27 | 2025-04-20 | 2025-05-20 | 30 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE |  | 0 |  | Update_010
Updates | TSK-060 | Task 060 | 2024-11-24 | 2025-02-22 | 2024-11-25 | 2024-12-28 | 33 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-061 | Task 061 | 2025-07-23 | 2025-08-03 | 2025-07-23 | 2025-08-07 | 15 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010
Updates | TSK-062 | Task 062 | 2025-05-12 | 2025-07-19 | 2025-05-09 | 2025-05-28 | 19 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_010
Updates | TSK-063 | Task 063 | 2024-12-26 | 2025-03-15 | 2024-12-24 | 2025-01-26 | 33 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-064 | Task 064 | 2025-05-20 | 2025-08-11 | 2025-05-22 | 2025-07-10 | 49 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-065 | Task 065 | 2025-01-02 | 2025-03-22 | 2025-01-03 | 2025-02-24 | 52 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE |  | 0 |  | Update_010
Updates | TSK-066 | Task 066 | 2024-11-08 | 2024-12-05 | 2024-11-09 | 2024-12-07 | 28 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-067 | Task 067 | 2025-03-05 | 2025-05-25 | 2025-03-05 | 2025-04-24 | 50 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-068 | Task 068 | 2025-05-21 | 2025-08-28 | 2025-05-23 | 2025-07-08 | 46 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | Low | 0 |  | Update_010
Updates | TSK-069 | Task 069 | 2025-05-29 | 2025-08-01 | 2025-05-31 | 2025-07-11 | 41 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | High | 0 |  | Update_010
Updates | TSK-070 | Task 070 | 2025-10-17 | 2026-01-15 | 2025-10-15 | 2025-12-05 | 51 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-071 | Task 071 | 2025-08-31 | 2025-10-21 | 2025-08-28 | 2025-10-09 | 42 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-072 | Task 072 | 2025-07-06 | 2025-09-01 | 2025-07-09 | 2025-08-09 | 31 | FALSE | 0 | 0 | 100% | Complete | TRUE | FALSE | FALSE | H | 0 |  | Update_010
Updates | TSK-073 | Task 073 | 2025-02-20 | 2025-05-02 | 2025-02-18 | 2025-03-10 | 20 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE | Medium | 0 |  | Update_010
Updates | TSK-074 | Task 074 | 2025-07-03 | 2025-09-28 | 2025-06-30 | 2025-08-04 | 35 | FALSE | 0 | 0 | 100% | Complete | FALSE | TRUE | FALSE | L | 0 |  | Update_010
Updates | TSK-075 | Task 075 | 2025-02-11 | 2025-04-01 | 2025-02-08 | 2025-03-25 | 45 | FALSE | 0 | 0 | 100% | Complete | FALSE | FALSE | FALSE |  | 0 |  | Update_010